## MVP WBS
Work Package | Description | Primary Skill | Person-Months (PM) | Depends On | Scenario
Architecture & tech setup | Initial architecture, repo/CI, coding standards. | Senior backend/architect | 6 | Start | MVP
3D kernel integration | OpenCascade/FreeCAD core integration, boolean ops, constraints. | C++/Python/CAD | 18 | Architecture | MVP
Parametric modeler (panels/assemblies) | Parametric cabinetry primitives, constraints, joints. | Geometry/algorithms | 20 | 3D kernel | MVP
Materials & hardware DB | CRUD, pricing, suppliers, units. | Backend/DB | 10 | Architecture | MVP
BOM & cutlist generator | Explode assemblies, unit conversions, reports. | Backend/algorithms | 8 | Parametric modeler | MVP
2D nesting (guillotine) + DXF export | Panel optimization, kerf, sawblade width, export. | Algorithms/CAM | 12 | Cutlist | MVP
Frontend UI/UX | Projects, 3D viewer (Three.js), editors, settings. | React/Three.js | 16 | Architecture | MVP
Import/Export basics | CSV/XLSX/DXF in+out. | Backend/Frontend | 6 | BOM/Nesting | MVP
Persistence & versioning | Save/load projects, migrations. | Backend/DB | 6 | Architecture | MVP
Testing & QA automation | Unit/integration tests, E2E. | QA/Dev | 8 | Cross-cutting | MVP
DevOps & packaging | CI/CD, installers, crash reporting. | DevOps | 4 | Architecture | MVP
Product & PM | Backlog, specs, triage, releases. | PM/BA | 6 | Start | MVP

## V1 WBS
Work Package | Description | Primary Skill | Person-Months (PM) | Depends On | Scenario
Advanced nesting | True-shape nesting, grain, part rotation rules. | Algorithms | 16 | MVP nesting | V1
Hardware rules engine | Auto-placements for hinges, slides, dowels. | Backend/geometry | 12 | Parametric modeler | V1
CAM/Postprocessors (2 CNCs) | Toolpaths, G-code for 2 controllers. | CAM/NC | 18 | MVP export | V1
Constraints & param templates | Param libraries, variants, error checks. | Geometry/UX | 10 | Parametric modeler | V1
Library manager | Templates, materials/hardware catalogs. | Full-stack | 8 | MVP DB | V1
User permissions & multi-project | Teams, roles. | Backend | 6 | MVP persistence | V1
Performance & memory work | Large assemblies optimization. | C++/Perf | 10 | 3D kernel | V1
Localization & units | i18n, imperial/metric. | Frontend | 4 | MVP UI | V1
QA, docs, onboarding | Guides, samples. | QA/Docs | 6 | Cross-cutting | V1

## Parity WBS
Work Package | Description | Primary Skill | Person-Months (PM) | Depends On | Scenario
More postprocessors (8+) | Controller coverage and config UI. | CAM/NC | 24 | V1 CAM | Parity
Auto-dimensioned drawings | 2D shop drawings, annotations. | CAD/TechDraw | 14 | Parametric/constraints | Parity
Advanced joinery | Dovetails, dados, mortise-tenon. | Geometry | 12 | Parametric modeler | Parity
ERP/MES integrations | 1C/SAP/Odoo connectors. | Integrations | 12 | Libraries/DB | Parity
Plugin SDK | Scripting, API, sandbox. | Platform | 10 | Core stabilized | Parity
Configurator CPQ | Rules + pricing + quotes. | Backend/UX | 12 | Libraries | Parity
Mobile viewer | Read-only 3D viewer, checklists. | Mobile/React Native | 8 | API | Parity
Compliance & licensing | Licensing server, telemetry. | Platform/Sec | 10 | Core stabilized | Parity
Hardening & certification | Installers, security, privacy. | Security/QA | 10 | Late stage | Parity

## Duration Scenarios
Scenario | Total PM | Juniors | Seniors | Estimated Duration (months)
MVP | 120 | 10 | 0 | 24
MVP | 120 | 10 | 2 | 17.1
MVP | 120 | 6 | 2 | 24
MVP | 120 | 8 | 1 | 24
V1 | 90 | 10 | 0 | 18
V1 | 90 | 10 | 2 | 12.9
V1 | 90 | 6 | 2 | 18
V1 | 90 | 8 | 1 | 18
Parity | 112 | 10 | 0 | 22.4
Parity | 112 | 10 | 2 | 16
Parity | 112 | 6 | 2 | 22.4
Parity | 112 | 8 | 1 | 22.4